## GANTT CHART
|  | Project Start |  | 2021-01-16
|  | Display Week: |  | 0 |  | 2021-01-04 | [6 empty] | 2021-01-11 | [6 empty] | 2021-01-18 | [6 empty] | 2021-01-25 | [6 empty] | 2021-02-01 | [6 empty] | 2021-02-08 | [6 empty] | 2021-02-15 | [6 empty] | 2021-02-22 | [6 empty] | 2021-03-01 | [6 empty] | 2021-03-08 | [6 empty] | 2021-03-15 | [6 empty] | 2021-03-22 | [6 empty] | 2021-03-29 | [6 empty] | 2021-04-05 | [6 empty] | 2021-04-12 | [6 empty] | 2021-04-19 | [6 empty] | 2021-04-26 | [6 empty] | 2021-05-03 | [6 empty] | 2021-05-10 | [6 empty] | 2021-05-17 | [6 empty] | 2021-05-24 | [6 empty] | 2021-05-31 | [6 empty] | 2021-06-07 | [6 empty] | 2021-06-14 | [6 empty] | 2021-06-21 | [6 empty] | 2021-06-28 | [6 empty] | 2021-07-05 | [6 empty] | 2021-07-12 | [6 empty] | 2021-07-19 | [6 empty] | 2021-07-26 | [6 empty] | 2021-08-02 | [6 empty] | 2021-08-09 | [6 empty] | 2021-08-16 | [6 empty] | 2021-08-23 | [6 empty] | 2021-08-30 | [6 empty] | 2021-09-06 | [6 empty] | 2021-09-13 | [6 empty] | 2021-09-20 | [6 empty] | 2021-09-27 | [6 empty] | 2021-10-04 | [6 empty] | 2021-10-11 | [6 empty] | 2021-10-18 | [6 empty] | 2021-10-25 | [6 empty] | 2021-11-01 | [6 empty] | 2021-11-08 | [6 empty] | 2021-11-15 | [6 empty] | 2021-11-22 | [6 empty] | 2021-11-29 | [6 empty] | 2021-12-06 | [6 empty] | 2021-12-13 | [6 empty] | 2021-12-20 | [6 empty] | 2021-12-27 | [6 empty] | 2022-01-03 | [6 empty] | 2022-01-10 | [6 empty] | 2022-01-17 | [6 empty] | 2022-01-24 | [6 empty] | 2022-01-31 | [6 empty] | 2022-02-07
 | time axis 2021-01-04 to 2022-02-13
TASK | Members | PROGRESS | NOTES | START | END | time axis 2021-01-04 to 2022-02-13
DSP
Develop a Gantt Chart | Nicholas | 100% |  | 2020-08-24 | 2020-09-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Turn node 3 back on | Kyle, Michael | 100% |  | 2020-08-28 | 2020-09-23
Setting Up VMs | Dennis, Dylan | 100% |  | 2020-09-20 | 2020-11-24
Modulation Overview | Nicholas | 100% |  | 2020-09-22 | 2020-10-13
Code Review | Pratik | 80% |  | 2020-09-23 | 2020-11-17
Simulink Multipath | Sarkis | 95% |  | 2020-09-23 | 2020-11-17
Run Tests on B210 | Michael | 100% |  | 2020-09-25 | 2020-10-05
Farrow Filters for TDOA | Kyle | 85% |  | 2020-09-28 | 2020-11-20
Cross Correlation of short sequence in FPGA | Michael, Nicholas | 90% |  | 2020-09-29 | 2020-11-13
Setup X310 | Michael, Nicholas | 0% |  | 2020-11-13 | 2020-11-27
Introduction to DSSS | Nicholas | 100% |  | 2020-10-27 | 2020-11-10
Openvpn Setup | Dylan | 0% |  | 2021-02-01 | 2021-02-15
HDL FFT Algorithm | Nicholas, James | 0% |  | 2001-02-15 | 2021-03-25
VHDL Code Review | James | 10% |  | 2021-03-15 | 2021-03-25
SOS
check on idc4 | CB | 100% |  | 2020-08-28 | 2020-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
test specrec command functionality | AJ, CB, KW | 100% |  | 2020-08-29 | 2020-10-16
Scheduling page and envoy | AJ | 100% |  | 2020-10-30 | 2020-11-20
attach pi to DJI drone & see communications | Akhil, Dylan | 0% |  | 2020-08-30 | 2020-09-06
csv upload | Chengkai | 100% |  | 2020-08-31 | 2020-09-28
ui descriptions | Shaohua | 100% |  | 2020-08-31 | 2020-09-10
Website database connection (writable) | CB | 100% |  | 2020-09-07 | 2020-09-21
Check node status script | Dylan | 75% |  | 2020-09-08 | 2020-09-22
Password manager | Dylan, Nicholas | 0% |  | 2020-09-10 | 2020-09-24
fix scheduling start time to local time | CB | 100% |  | 2020-09-14 | 2020-09-30
ReadMe update to new wiki | Shaohua | 100% |  | 2020-10-02 | 2020-10-16
stadium checklist | Akhil, Kyle | 100% |  | 2020-10-09 | 2020-10-23
New table for nodes, refactoring | Chengkai, Shaohua | 100% |  | 2020-10-16 | 2020-11-15
Check on rfsn1 and rfsn2 | Akhil | 100% |  | 2021-01-20 | 2021-01-28
Hypervisor documentation | Dylan, Nicholas | 0% |  | 2021-01-20 | 2021-03-25
Merge envoy to master | AJ | 100% |  | 2021-01-20 | 2021-03-25
Organization of data | Dylan | 10% | on hold | 2021-01-20 | 2021-03-25
Learn Laravel | Bryan | 100% |  | 2021-01-20 | 2021-03-25
Node status integrated in website | Casey | 40% |  | 2021-01-20 | 2021-03-25
General documentation/GitHub wiki testing | Dylan | 0% |  | 2021-01-28 | 2021-03-25
laravel password protection | Bryan | 100% |  | 2021-02-11 | 2021-03-25
Environment Setup | Kyle Waldner | 100% |  | 2021-01-28 | 2021-02-04
More info on landing page | Kyle Waldner | 100% |  | 2021-02-04 | 2021-03-25
Wiki cleanup | Akhil, Dylan, Kyle Watters, everyone | 0% |  | 2021-02-04 | 2021-03-25
Test with drone in stadium | Akhil | 0% |  | 2021-02-04 | 2021-03-25
Certification of website through GT | Dylan, Kyle Waldner |  |  | 2021-02-11 | 2021-03-25
Use spectrum analyzer on drone, document | Akhil, Dennis | 100% |  | 2021-02-04 | 2021-03-25
Bash script logic changes (add segsize as a variable, regulate master clock rate) | Casey | 100% |  | 2021-02-11 | 2021-03-25
Add comments field for recordings | Kyle Waldner | 100% |  | 2021-02-11 | 2021-03-25
Functionality to edit/cancel recordings | AJ, Bryan | 0% |  | 2021-03-25
Validate against recordings at the same time/overlapping time | Kyle Waldner | 80% |  | 2021-03-11
Update Envoy documentation | AJ | 100% |  | 2021-03-04 | 2021-03-12